## Estimate
Task | Milestone | Total, hr. | Front view, hr. | Front logic, hr. | Back api, hr. | Back logic, hr. | Database, hr. | Testing, hr. | Automation test, hr. | Docs, hr. | UI Design, hr. | Management, hr. | Risk, hr. | Historical ref. | Confidence
Create a script to extract data from receipts/invoices in various formats (PDF, JPEG, PNG, HEIC) using OCR and NLP. | Data Extraction | 20.5 | 3 | 4 | 4 | 3 | 1 | 1 | 0 | 1 | 1 | 0.5 | 2 | Export transaction history to PDF | medium
Implement data encryption using AES-256 and ensure GDPR compliance. | Security | 11 | 0 | 0 | 3 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | Data encryption for sensitive fields | medium
Develop a Python-based CLI tool or Docker container for the script. | Development | 13.5 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 2.5 | 1 | CI/CD pipeline setup (GitHub Actions) | medium
Deploy the script on AWS Lambda or a local Ubuntu server. | Deployment | 9.5 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 1.5 | 1 | Production environment setup (AWS) | medium
Set up user roles and permissions for operators, admins, and system accounts. | User Management | 12.5 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0.5 | 2 | Admin role permission management | medium
Integrate with Google Cloud Vision API or AWS Textract for OCR. | Integration | 13.5 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 1 | 0.5 | Google Maps API for service locations | medium
Sync extracted data with QuickBooks or Xero via REST APIs. | Integration | 12.7 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5 | Offline caching of last bills/receipts (read-only) | medium
Store extracted data in a relational SQL database and archive original files in an S3 bucket. | Data Storage | 12.7 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5 | Offline caching of last bills/receipts (read-only) | medium
Design a minimalist CLI with progress bars and summary report. | UI/UX | 13 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.5 | 0.5 | Generate bill preview from readings (client-side calc stub) | medium
Manage deployment with a Git-based workflow and .env files. | Deployment Management | 3.5 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | Env configs + secrets handling | medium