## HistoricalData
Name | Description | Estimation (Hours) | Date
Project Initialization | Set up the initial Git repository structure and configure branch protection rules for the team | 2 | 2025-09-01
CI/CD Pipeline Setup | Configure automated build and linting pipelines to ensure code quality before merging | 4 | 2025-09-01
Database Schema Design | Analyze requirements and design the Entity Relationship Diagram for the core database tables | 6 | 2025-09-02
Database Environment Setup | Initialize the PostgreSQL database container with Docker and apply initial configuration | 3 | 2025-09-02
Authentication Module | Create the basic directory structure and module configuration for user authentication | 2 | 2025-09-03
User Registration Logic | Implement the backend service to handle new user sign-ups including data validation | 5 | 2025-09-03
Security Implementation | Integrate password hashing algorithms to securely store user credentials | 3 | 2025-09-04
Token Management | Set up JWT generation and validation strategies to secure API endpoints | 4 | 2025-09-04
Login Functionality | Develop the logic to verify user credentials and issue access tokens upon successful login | 5 | 2025-09-05
User Profile Retrieval | Implement functionality to retrieve and display the current user's profile information | 2 | 2025-09-05
Frontend Setup | Initialize the client-side application using React and configure the build tools | 2 | 2025-09-08
UI Theme Configuration | Set up the design system and configure the global color palette and typography | 4 | 2025-09-08
Login Screen UI | Design and implement the user interface for the login page with error handling | 6 | 2025-09-09
Registration Screen UI | Create the user registration form with client-side validation for all inputs | 6 | 2025-09-09
State Management Setup | Configure the global state store to manage user authentication status | 3 | 2025-09-10
Auth Integration | Connect the frontend login and registration forms to the backend API services | 5 | 2025-09-10
Cross-Origin Config | Configure CORS policies to allow secure communication between frontend and backend | 1 | 2025-09-11
Dashboard Layout | Build the main application shell including the sidebar navigation and header | 8 | 2025-09-12
Product Data Model | Define the database entities and relationships required for product management | 2 | 2025-09-15
Product Management API | Develop the backend endpoints to create read update and delete products | 8 | 2025-09-15
Data Seeding | Create a script to populate the database with dummy data for development purposes | 2 | 2025-09-16
Product Catalog UI | Develop the main grid view to display available products to the user | 6 | 2025-09-17
Filtering Logic | Implement backend logic to filter database results based on category and price range | 5 | 2025-09-18
Filter Sidebar UI | Create the user interface controls for filtering the product list | 4 | 2025-09-18
Auth Unit Testing | Write unit tests to verify the correctness of the authentication service logic | 4 | 2025-09-19
Product Unit Testing | Write unit tests to ensure product management business logic handles edge cases | 4 | 2025-09-19
E2E Test Environment | Set up the end-to-end testing framework to simulate real user scenarios | 3 | 2025-09-22
Login Persistence Fix | Resolve an issue where the user session was not persisting after page reload | 2 | 2025-09-22
Code Refactoring | Refactor the user controller to improve code readability and reduce duplication | 1 | 2025-09-23
Order Data Model | Design the database tables to store order information and order items | 3 | 2025-09-23
Order Creation Logic | Implement the business logic to process a user's cart and generate a new order | 8 | 2025-09-24
Cart Storage Backend | Set up a temporary storage mechanism (Redis) to hold user shopping cart items | 5 | 2025-09-25
Cart Drawer UI | Develop a sliding drawer component to show the contents of the shopping cart | 6 | 2025-09-26
Add to Cart Feature | Implement the frontend logic to add products to the global cart state | 3 | 2025-09-26
Order History Service | Create the backend service to retrieve a list of past orders for a specific user | 3 | 2025-09-29
Order History Page | Design the frontend page to display a table of the user's previous orders | 5 | 2025-09-29
Payment Integration | Integrate the third-party payment gateway to handle secure credit card transactions | 13 | 2025-09-30
Payment Webhooks | Implement a webhook handler to update order status upon successful payment | 5 | 2025-10-01
Calculation Fix | Fix a rounding error in the total price calculation logic for orders | 1 | 2025-10-02
Email Service Config | Configure the email provider integration for sending transactional emails | 3 | 2025-10-02
Welcome Emails | Implement logic to send a welcome email automatically after user registration | 2 | 2025-10-03
Order Receipts | Set up automated email receipts to be sent after a successful purchase | 3 | 2025-10-03
Admin Access Control | Implement role-based access control to restrict administrative routes | 2 | 2025-10-06
Admin Analytics UI | Create a dashboard view for admins showing key sales and user metrics | 8 | 2025-10-07
User Moderation Tools | Develop an interface for admins to view and ban suspicious user accounts | 5 | 2025-10-08
Product Editing UI | Create a form for administrators to modify existing product details | 6 | 2025-10-09
Image Uploads | Implement functionality to upload and store product images in cloud storage | 5 | 2025-10-10
Image Optimization | Set up a serverless function to automatically resize images for better performance | 8 | 2025-10-13
Database Tuning | Analyze query performance and add necessary indexes to foreign key columns | 2 | 2025-10-14
Mobile Layout Fix | Fix layout issues preventing the application from rendering correctly on mobile devices | 3 | 2025-10-14
Performance Optimization | Audit the application bundle size and implement code splitting to improve load time | 4 | 2025-10-15
Route Lazy Loading | Refactor the routing configuration to load page components only when needed | 2 | 2025-10-15
API Documentation | Add comprehensive comments and decorators to generate Swagger API documentation | 6 | 2025-10-16
Rate Limiting | Configure API rate limiting to prevent abuse and denial of service attacks | 2 | 2025-10-17
Logging Infrastructure | Set up a centralized logging system to track errors and application events | 5 | 2025-10-20
Cart Bug Fix | Fix a critical bug where the cart would empty itself unexpectedly | 2 | 2025-10-21
Auth Middleware Refactor | Simplify the authentication middleware to make it more maintainable | 1 | 2025-10-21
Search Backend | Implement full-text search capabilities to allow finding products by name or description | 6 | 2025-10-22
Search Component | Create a search bar with auto-suggestion capabilities for the frontend | 3 | 2025-10-23
Real-time Notifications | Set up a WebSocket gateway to push real-time updates to connected clients | 8 | 2025-10-24
Notification Toasts | Implement a UI component to display ephemeral success and error messages | 4 | 2025-10-27
Staging Deployment | Configure the deployment pipeline to push the latest build to the staging server | 3 | 2025-10-28
Staging Smoke Test | Perform a manual pass through critical user flows on the staging environment | 2 | 2025-10-28
Migration Fix | Resolve a database migration conflict causing deployment failures | 1 | 2025-10-29
Security Audit | Review and rotate all sensitive environment variables and API keys | 1 | 2025-10-29
Code Review | Review pull requests from the team to ensure code standards are met | 5 | 2025-10-30
Sprint Planning | Participate in the team meeting to estimate tasks for the upcoming sprint | 1 | 2025-10-30
Design Sync | Meet with the design team to review high-fidelity mockups for new features | 2 | 2025-10-31
Dependency Update | Update core framework dependencies to their latest stable versions | 3 | 2025-11-03
Deprecation Fixes | Resolve console warnings caused by deprecated methods in updated libraries | 2 | 2025-11-03
Accessibility Review | Audit the application forms to ensure they meet WCAG 2.1 accessibility standards | 4 | 2025-11-04
Aria Labels | Add missing accessibility labels to icon-only buttons throughout the app | 1 | 2025-11-04
Integration Testing | Write tests to verify the data flow from the cart to order creation | 5 | 2025-11-05
Load Testing | Perform stress testing on the API to determine maximum concurrent user capacity | 6 | 2025-11-06
Caching Strategy | Implement Redis caching for high-traffic API endpoints to reduce latency | 3 | 2025-11-07
SEO Optimization | Update meta tags and favicon to improve search engine visibility | 1 | 2025-11-07
Error Pages | Design and implement custom 404 and 500 error pages | 2 | 2025-11-10
Feedback System | Create a form allowing users to submit feedback or report bugs | 3 | 2025-11-11
Feedback Storage | Develop an API endpoint to store user feedback in the database | 2 | 2025-11-11
Dark Mode Logic | Implement a theme provider to toggle between light and dark visual modes | 5 | 2025-11-12
Dark Mode Styling | Fix contrast issues and unreadable text when dark mode is enabled | 2 | 2025-11-13
Localization Setup | Configure the internationalization framework to support multiple languages | 4 | 2025-11-14
Translation Updates | Extract hardcoded text strings and replace them with translation keys | 3 | 2025-11-17
Avatar Upload | Add functionality for users to upload and crop a profile picture | 3 | 2025-11-18
Password Change | Implement a secure form for authenticated users to change their password | 4 | 2025-11-19
Password Recovery | Develop the backend logic to generate and email password reset tokens | 5 | 2025-11-20
Reset Page UI | Create the frontend page where users input their new password | 3 | 2025-11-21
Analytics Validation | Verify that user events are being correctly sent to the analytics platform | 2 | 2025-11-24
Z-Index Fix | Resolve visual layering issues where modals appear behind the header | 1 | 2025-11-24
CSS Modularization | Refactor global CSS styles into modular components to prevent bleeding | 3 | 2025-11-25
Backup Automation | Create a cron job to automatically backup the database to S3 nightly | 2 | 2025-11-26
Uptime Monitoring | Configure external monitoring tools to alert the team in case of downtime | 2 | 2025-11-27
Legal Pages | Create static pages for Terms of Service and Privacy Policy | 1 | 2025-11-27
Cookie Banner | Implement a GDPR-compliant cookie consent banner | 2 | 2025-11-28
Pre-release QA | Conduct a comprehensive round of manual testing before the production release | 8 | 2025-12-01
Checkout Bug Fix | Fix an edge case where the checkout crashes if the cart contains 0 items | 3 | 2025-12-02
Documentation | Update the project README and developer guides with latest instructions | 2 | 2025-12-03
Release Notes | Draft the change log and release notes for version 1.0 | 2 | 2025-12-04
Production Launch | Execute the deployment strategy to release version 1.0 to the public | 4 | 2025-12-05