## Sheet1
Task | Milestone | Total, hr. = 300 | Front view, hr. | Front logic, hr. | Back api, hr. | Back logic, hr. | Database, hr. | Testing, hr. | Automation test, hr. | Docs, hr. | UI Design, hr. | Management, hr. | Risk, hr.
Project kickoff & requirements workshop (utilities tracking & payments) | Discovery & Planning | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
Define MVP scope + acceptance criteria (providers, bills, payments) | Discovery & Planning | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
User flow mapping (accounts â bills â payment â history) | Discovery & Planning | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
Low-fidelity wireframes (dashboard, bill details, pay flow) | Discovery & Planning | 9 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1
React Native bootstrap + repo setup | Setup | 6 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Lint/format + git hooks | Setup | 4.5 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Navigation base structure | Setup | 6.5 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
State management base store | Setup | 5.5 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
API client + interceptors | Setup | 5.5 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Env configs + secrets handling | Setup | 3.5 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Login/Sign-up screens (phone/email) | Auth & KYC-lite | 15.5 | 8 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.5
OTP verification / password reset flows | Auth & KYC-lite | 13 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.5 | 0.5
Token auth + secure storage | Auth & KYC-lite | 9.5 | 0 | 0 | 8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5
Session persistence + logout + refresh token flow | Auth & KYC-lite | 10.7 | 0 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5
Dashboard: current balance + due bills + quick actions | Core Billing | 25.5 | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 0.5
Bills list screen (by provider, due date, status) | Core Billing | 19.5 | 8 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Bill details screen (meter, period, amount, breakdown) | Core Billing | 21.5 | 8 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Provider management (add/remove utility accounts) | Core Billing | 19.5 | 6 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Meter readings input (manual entry) + validation | Core Billing | 21.5 | 6 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Generate bill preview from readings (client-side calc stub) | Core Billing | 13 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.5 | 0.5
Payment flow UI (choose bill â amount â confirm) | Payments | 24.5 | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0.5
Integrate payment gateway SDK (Apple Pay / Google Pay / cards) | Payments | 23 | 0 | 0 | 18 | 0 | 0 | 0 | 4 | 0 | 0 | 0.5 | 0.5
3DS / payment authentication handling + edge cases | Payments | 19 | 0 | 0 | 14 | 0 | 0 | 0 | 4 | 0 | 0 | 0.5 | 0.5
Payment status screen (success/fail/pending) + receipt view | Payments | 19.5 | 6 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Transaction history screen + filters | Payments | 21.5 | 8 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Save payment methods (tokenized) + manage list | Payments | 21.5 | 6 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
Push notifications setup + token register | Notifications | 17.7 | 0 | 0 | 14 | 0 | 0 | 0 | 3 | 0 | 0 | 0.2 | 0.5
Bill reminders (due soon / overdue) + deep links | Notifications | 17.7 | 4 | 0 | 10 | 0 | 0 | 0 | 3 | 0 | 0 | 0.2 | 0.5
Offline caching of last bills/receipts (read-only) | Offline & Security | 12.7 | 0 | 0 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5
Security hardening (biometric lock, secure screens) | Offline & Security | 18.7 | 4 | 0 | 12 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5
PII-safe logging + privacy controls | Offline & Security | 8.7 | 0 | 0 | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 0.2 | 0.5
Global error handling + loaders + empty states | Quality | 22.8 | 8 | 0 | 10 | 0 | 0 | 0 | 4 | 0 | 0 | 0.3 | 0.5
Basic analytics events (bill viewed, payment started/completed) | Quality | 7.7 | 0 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0.5
Crash reporting setup (Sentry/Firebase) | Quality | 4.7 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0.5
QA pass + bug fixing buffer | QA & Release | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 2
Store-ready config (icons, splash, permissions, privacy policy links) | QA & Release | 16 | 4 | 0 | 8 | 0 | 0 | 0 | 3 | 0 | 0 | 0.5 | 0.5
Release candidate build + handover docs | QA & Release | 14 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 6 | 2
Change password screen & logic | User Profile | 14 | 4 | 2 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 1.5 | 0.5
Forgot password flow (email link) | User Profile | 19.5 | 3 | 4 | 3 | 2 | 2 | 1 | 0 | 1 | 1 | 0.5 | 2
Edit profile details (name, phone) | User Profile | 17.5 | 4 | 2 | 3 | 2 | 2 | 1 | 0 | 0 | 1 | 1.5 | 1
Biometric login (FaceID/TouchID) integration | User Profile | 13 | 3 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 1.5 | 0.5
App theme settings (Dark/Light mode) toggle | User Profile | 13 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0.5 | 0.5
Language localization setup | User Profile | 11.5 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1.5 | 1
Terms of Service & Privacy Policy static pages | User Profile | 15.5 | 4 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 0.5 | 1
Delete account request & logic | User Profile | 15.5 | 2 | 3 | 2 | 2 | 0 | 2 | 0 | 1 | 2 | 1 | 0.5
Monthly spending bar chart component | Analytics | 15.5 | 5 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 1.5 | 1
Spending category breakdown (Pie chart) | Analytics | 12 | 2 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 1 | 1
Backend aggregation for monthly stats | Analytics | 11.5 | 0 | 0 | 3 | 3 | 1 | 1 | 0 | 0.5 | 0 | 1 | 2
Year-over-year comparison logic | Analytics | 17.5 | 0 | 0 | 3 | 6 | 3 | 2 | 0 | 0.5 | 0 | 1 | 2