## Sheet1
Task | Milestone | Total, hr. = 300 | Front view, hr. | Front logic, hr. | Back api, hr. | Back logic, hr. | Database, hr. | Testing, hr. | Automation test, hr. | Docs, hr. | UI Design, hr. | Management, hr. | Risk, hr.
Usage trends analysis (units consumed) | Analytics | 20 | 3 | 4 | 4 | 3 | 1 | 2 | 0 | 1 | 0 | 1.5 | 0.5
Search providers screen with autocomplete | Provider Management | 18 | 5 | 5 | 0 | 0 | 0 | 2 | 0 | 0.5 | 3 | 0.5 | 2
Backend API for provider search | Provider Management | 13.5 | 0 | 0 | 2 | 4 | 2 | 1 | 0 | 1 | 0 | 1.5 | 2
Manual bill entry form | Provider Management | 12 | 2 | 5 | 0 | 0 | 0 | 2 | 0 | 0.5 | 1 | 1 | 0.5
Scan QR code on bill (camera integration) | Provider Management | 12 | 2 | 4 | 0 | 0 | 0 | 1 | 0 | 0.5 | 2 | 1.5 | 1
Update provider credentials flow | Provider Management | 18.5 | 3 | 3 | 2 | 4 | 1 | 1 | 0 | 1 | 1 | 0.5 | 2
Unlink provider logic | Provider Management | 12 | 0 | 0 | 2 | 4 | 1 | 1 | 0 | 0.5 | 0 | 1.5 | 2
FAQ list screen & data structure | Support | 16.5 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1.5 | 1
Contact support form | Support | 12.5 | 4 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 1
Backend for support ticket creation | Support | 13.5 | 0 | 0 | 2 | 6 | 1 | 2 | 0 | 0.5 | 0 | 1.5 | 0.5
Intercom/Chat widget integration | Support | 14 | 4 | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 1 | 1
Onboarding tutorial slider (first launch) | Support | 17 | 5 | 5 | 0 | 0 | 0 | 2 | 0 | 0.5 | 2 | 0.5 | 2
Admin portal login page | Admin Panel | 11.5 | 3 | 2 | 0 | 0 | 0 | 2 | 0 | 0.5 | 3 | 0.5 | 0.5
Admin dashboard overview | Admin Panel | 12 | 2 | 3 | 0 | 0 | 0 | 2 | 0 | 0.5 | 2 | 1.5 | 1
User management table (list, search) | Admin Panel | 19.5 | 2 | 3 | 4 | 3 | 1 | 2 | 0 | 1 | 1 | 0.5 | 2
User details view (admin) | Admin Panel | 19.5 | 4 | 2 | 4 | 3 | 0 | 1 | 0 | 0.5 | 2 | 1 | 2
Provider management (CRUD) | Admin Panel | 15 | 2 | 4 | 2 | 2 | 0 | 2 | 0 | 1 | 1 | 0.5 | 0.5
View system logs interface | Admin Panel | 10 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0.5 | 1 | 0.5 | 2
Log aggregation API endpoints | Admin Panel | 16 | 0 | 0 | 2 | 7 | 1 | 2 | 0 | 0.5 | 0 | 1.5 | 2
Broadcast push notification tool | Admin Panel | 20 | 2 | 4 | 3 | 3 | 1 | 1 | 0 | 1 | 2 | 1 | 2
Admin role permission management | Admin Panel | 12.5 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0.5 | 2
CI/CD pipeline setup (GitHub Actions) | Infrastructure | 13.5 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 2.5 | 1
Staging environment configuration | Infrastructure | 8 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 1.5 | 0.5
Production environment setup (AWS) | Infrastructure | 9.5 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 1.5 | 1
Database backup & restore scripts | Infrastructure | 9 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 3.5 | 0.5
Monitoring setup (Sentry/Datadog) | Infrastructure | 13.5 | 0 | 0 | 0 | 7 | 0 | 2 | 0 | 0 | 0 | 3.5 | 1
Email service integration (SendGrid/SES) | Integration | 13.5 | 0 | 0 | 5 | 4 | 2 | 1 | 0 | 0.5 | 0 | 0.5 | 0.5
SMS gateway integration (Twilio) | Integration | 13 | 0 | 0 | 4 | 4 | 2 | 1 | 0 | 0.5 | 0 | 1 | 0.5
Google Maps API for service locations | Integration | 13.5 | 4 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 1 | 0.5
Social Login (Google) | Integration | 17.5 | 3 | 2 | 4 | 3 | 1 | 1 | 0 | 1 | 0 | 0.5 | 2
Social Login (Apple) | Integration | 16 | 2 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0.5 | 0.5
API Rate limiting implementation | Security | 13.5 | 0 | 0 | 5 | 4 | 1 | 1 | 0 | 0.5 | 0 | 1.5 | 0.5
Input validation & sanitization review | Security | 11.5 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 0 | 0 | 1.5 | 2
JWT token refresh mechanism | Security | 15 | 0 | 0 | 2 | 6 | 3 | 2 | 0 | 0.5 | 0 | 0.5 | 1
Data encryption for sensitive fields | Security | 11 | 0 | 0 | 3 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 1
Animation & Transitions for navigation | Polish | 14 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 1
Accessibility improvements (aria labels) | Polish | 15.5 | 3 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 0.5 | 2
Tablet responsiveness adjustments | Polish | 14.5 | 5 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0.5 | 1
Loading states & skeletons for all screens | Polish | 9 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2
Error handling & empty states UI | Polish | 16 | 5 | 5 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1
Unit tests for calculation logic | Testing | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0.5 | 0.5
Integration tests for payment flow | Testing | 12 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 1 | 2
E2E tests (Cypress/Detox) setup | Testing | 14 | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 0 | 0 | 0.5 | 0.5
E2E critical path coverage | Testing | 10 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 1.5 | 0.5
Performance profiling & optimization | Testing | 14.5 | 0 | 0 | 0 | 0 | 0 | 11 | 2 | 0 | 0 | 0.5 | 1
Security audit & fix | Testing | 8.5 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0.5 | 1
App Store screenshots & metadata | Release | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4.5 | 2
Google Play Store submission prep | Release | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 7.5 | 0.5